ServiceM8 Add-On:

“Send for Signature” via Docusign

Project Plan & Cost Estimate

Prepared by: SPXPERT Solutions

September 2026

# Contents

Contents	2

1. Scope Recap	3

2. Task Breakdown	3

3. Timeline	3

4. Cost Estimate	3

4.1 One-time build cost	3

4.2 Recurring platform costs	4

5. Open Questions	4

# 1. Scope Recap

A button added to the ServiceM8 Job card (“Send for Signature”). Clicking it builds a DocuSign envelope from a pre-built contract template, pre-filled with the job address, description and reference, and sends it to the job contact for e-signature. On completion, the signed PDF is attached back to the Job Diary automatically, with status notes for sent, completed, declined and voided outcomes.

# 2. Task Breakdown

| # | Task | Duration |
| --- | --- | --- |
| 1 | DocuSign account setup: Integration Key, RSA keypair, one-time admin consent grant, build the contract template with signer role and text tabs (JobAddress, JobDescription, JobReference) | 1 day |
| 2 | ServiceM8 Add-on registration: manifest, App Secret, action button wiring on the Job entity | 0.5 day |
| 3 | Send-envelope handler: verify inbound action JWT, resolve job + job contact via ServiceM8 API, build and send the envelope, write confirmation Note back to the Job Diary | 1.5 days |
| 4 | DocuSign Connect webhook handler: receive status-change events, attach signed PDF to the Job on completion, write status Notes for declined/voided | 1 day |
| 5 | Multi-template routing (only if job categories need different contracts — to confirm) | 0.5–1 day, conditional |
| 6 | End-to-end testing in DocuSign's sandbox + a ServiceM8 test account: send, sign, decline, and missing-contact-email paths | 1 day |
| 7 | Deployment: secrets into Key Vault, switch to production DocuSign account, go live | 0.5 day |

Total build effort: 5.5–7 development days (add the 0.5–1 day for task 5 only if multiple contract templates are needed — flagged as an open question in the design review).

# 3. Timeline

| Week | Focus |
| --- | --- |
| Week 1 | DocuSign account/template setup and Add-on registration (tasks 1–2) run in parallel with the start of the send-envelope handler (task 3) |
| Week 1–2 | Complete the send-envelope handler and build the Connect webhook handler (tasks 3–4) |
| Week 2 | Testing and go-live (tasks 6–7) |

Elapsed time: roughly 2 calendar weeks, assuming the DocuSign admin consent grant (a five-minute action for whoever administers the client's DocuSign account) happens promptly in week 1 — this is the one step that depends on someone outside the build team and is worth scheduling early rather than leaving until testing.

Since this Add-on is for a single client's own account rather than a public marketplace listing, it does not need to go through DocuSign App Review or ServiceM8's Add-on Store review process — both of those apply to listed/public integrations, not private ones. That keeps the 2-week timeline realistic; a public listing on either platform would add review time on top.

# 4. Cost Estimate

## 4.1 One-time build cost

As with the earlier proposals, effort is given in development days rather than a fixed fee — apply your standard day rate to the 5.5–7 day range above. Can convert to a fixed-price figure once a rate is agreed.

## 4.2 Recurring platform costs

| Item | Typical cost | Notes |
| --- | --- | --- |
| DocuSign – production API access | Business Pro from ~$40/user/month, or a dedicated low-volume Developer API plan from roughly $50/month | DocuSign's plan/envelope pricing is not fully public and varies by negotiated terms — confirm exact cost and envelope allowance directly with a DocuSign account rep based on expected monthly send volume |
| ServiceM8 API/Add-on access | Included if already on a Developer-enabled plan | Same account already used for the Direct Debit and Meta Leads add-ons — no incremental cost expected |
| Hosting (integration service) | A few dollars/month, or $0 incremental | Can run alongside the existing Azure Function app already proposed for the other ServiceM8 automations rather than standing up a new one |

DocuSign's published consumer/business pricing is easy to find, but production API access and per-envelope allowances are quoted per-account and change depending on volume and contract terms — worth getting a direct quote from DocuSign before finalising the client's budget, rather than relying on the ranges above.

# 5. Open Questions

- Does every job type sign the same contract, or does the button need to choose between a few templates by job category? (drives task 5)

- Expected monthly envelope volume, to size the right DocuSign plan/tier.

- Who on the client side will complete the one-time DocuSign consent grant, and when — best scheduled in week 1.